## Slide 1
Research Schedule — Week 4 Update
June 23, 2026 · End of Phase 1, Phase 2 in progress
JUNE
JULY
AUGUST
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
✓
Phase 1
Setup & Architecture
Env. setup · Git · FastAPI base · Project structure
▶
Phase 2
OCR & Doc Processing
Tesseract · pdfplumber · OpenCV preprocessing · /upload route
IN PROGRESS
Phase 3
AI Categorization
Phase 4
Search & Database
Phase 5
Web Portal (React)
Phase 6
Testing & Deployment
TODAY
Completed
In progress
Not started

## Slide 2
Week 4 — Progress Update
SKMH Project · Seïf NASEF · June 23, 2026
✔
Phase 1 — Completed
Dev environment fully configured (Python, Node.js, Git, Tesseract, PostgreSQL)
GitHub repo created, project structure in place
FastAPI backend running with health check & /upload route
First successful OCR test on a real PDF document
Project architecture documented
⚙
Phase 2 — In Progress
OCR pipeline working for PDFs and images
OpenCV preprocessing integrated (contrast, noise removal)
pdfplumber added for native digital PDFs
Currently improving accuracy on low-quality scans
▶
Coming up — Phase 3
Implement document categorization with spaCy & scikit-learn
Train classifier on sample KUIC documents
Connect categorization output to database (Phase 4)
Week 4 review · KUIC — Bangkok 2026